## Field changes duration
Date of change | Updated by | Key | Key (Changes duration) | Issue Type | Issue Type (Changes duration) | Summary | Summary (Changes duration) | Assignee | Assignee (Changes duration) | Status | Status (Changed) | Status (Changes duration) | Due date | Due date (Changed) | Due date (Changes duration) | Priority | Priority (Changed) | Priority (Changes duration)
2026-04-24 11:49 |  | DEVS-48 | 91:05 | Task | 91:05 | Test failed and successful transactions | 91:05 | Emily Johnson | 91:05 | IN PROGRESS |  | 70:08 | 2026-06-30 |  | 91:05 | High |  | 91:05
2026-04-21 13:41 | Emily Johnson | DEVS-48 |  | Task |  | Test failed and successful transactions |  | Emily Johnson |  | TO DO | IN PROGRESS | 20:56 | 2026-06-30 |  |  | High
2026-04-20 16:44 | Emily Johnson | DEVS-48 |  | Task |  | Test failed and successful transactions |  | Emily Johnson |  | TO DO |  |  | 2026-06-30 |  |  | High
2026-04-24 11:49 |  | DEVS-47 | 91:05 | Task | 91:05 | Add payment history page | 91:05 | Cody Fisher | 91:05 | TO DO |  | 91:05 | 2026-05-22 |  | 91:05 | Low |  | 91:05
2026-04-20 16:43 | Emily Johnson | DEVS-47 |  | Task |  | Add payment history page |  | Cody Fisher |  | TO DO |  |  | 2026-05-22 |  |  | Low
2026-04-24 11:49 |  | DEVS-46 | 91:07 | Task | 91:07 | Implement subscription plans | 91:07 | Cody Fisher | 91:07 | TO DO |  | 91:07 | 2026-05-14 |  | 91:07 | Medium |  | 91:07
2026-04-20 16:42 | Cody Fisher | DEVS-46 |  | Task |  | Implement subscription plans |  | Cody Fisher |  | TO DO |  |  | 2026-05-14 |  |  | Medium
2026-04-24 11:49 |  | DEVS-45 | 91:08 | Task | 91:08 | Handle webhook events | 91:08 | Cody Fisher | 91:08 | IN PROGRESS |  | 91:08 | 2026-05-08 |  | 89:38 | Medium |  | 91:08
2026-04-20 18:11 | Cody Fisher | DEVS-45 |  | Task |  | Handle webhook events |  | Cody Fisher |  | IN PROGRESS |  |  | 2026-04-23 | 2026-05-08 | 1:30 | Medium
2026-04-20 16:41 | Cody Fisher | DEVS-45 |  | Task |  | Handle webhook events |  | Cody Fisher |  | TO DO | IN PROGRESS | 0:00 | 2026-04-23 |  |  | Medium
2026-04-20 16:41 | Emily Johnson | DEVS-45 |  | Task |  | Handle webhook events |  | Cody Fisher |  | TO DO |  |  | 2026-04-23 |  |  | Medium
2026-04-24 11:49 |  | DEVS-44 | 91:10 | Task | 91:10 | Create payment flow UI | 91:10 | Cody Fisher | 89:57 | IN PROGRESS |  | 91:10 | 2026-04-30 |  | 91:10 | High |  | 89:56
2026-04-20 17:52 | Emily Johnson | DEVS-44 |  | Task |  | Create payment flow UI |  | Cody Fisher |  | IN PROGRESS |  |  | 2026-04-30 |  |  | Medium | High | 1:13
2026-04-20 17:52 | Emily Johnson | DEVS-44 |  | Task |  | Create payment flow UI |  | Emily Johnson | 1:13 | IN PROGRESS |  |  | 2026-04-30 |  |  | Medium
2026-04-20 16:39 | Emily Johnson | DEVS-44 |  | Task |  | Create payment flow UI |  | Emily Johnson |  | TO DO | IN PROGRESS | 0:00 | 2026-04-30 |  |  | Medium
2026-04-20 16:39 | Emily Johnson | DEVS-44 |  | Task |  | Create payment flow UI |  | Emily Johnson |  | TO DO |  |  | 2026-04-30 |  |  | Medium
2026-04-24 11:49 |  | DEVS-43 | 91:14 | Epic | 91:14 | Bug Fixing & Stability Improvements | 91:14 | Emily Johnson | 91:14 | TO DO |  | 91:14 | 2026-12-31 |  | 91:13 | Medium |  | 91:14
2026-04-20 16:35 | Emily Johnson | DEVS-43 |  | Epic |  | Bug Fixing & Stability Improvements |  | Emily Johnson |  | TO DO |  |  |  | 2026-12-31 | 0:00 | Medium
2026-04-20 16:35 | Emily Johnson | DEVS-43 |  | Epic |  | Bug Fixing & Stability Improvements |  | Unassigned | 0:00 | TO DO | [5 empty] | Medium
2026-04-20 16:35 | Emily Johnson | DEVS-43 |  | Epic |  | Bug Fixing & Stability Improvements |  | Unassigned |  | TO DO | [5 empty] | Medium
2026-04-24 11:49 |  | DEVS-42 | 91:15 | Epic | 91:15 | Security & Compliance | 91:15 | Cody Fisher | 91:15 | TO DO |  | 91:15 | 2026-06-30 |  | 91:15 | Medium |  | 91:15
2026-04-20 16:34 | Emily Johnson | DEVS-42 |  | Epic |  | Security & Compliance |  | Cody Fisher |  | TO DO |  |  |  | 2026-06-30 | 0:00 | Medium
2026-04-20 16:34 | Emily Johnson | DEVS-42 |  | Epic |  | Security & Compliance |  | Unassigned | 0:00 | TO DO | [5 empty] | Medium
2026-04-20 16:34 | Emily Johnson | DEVS-42 |  | Epic |  | Security & Compliance |  | Unassigned |  | TO DO | [5 empty] | Medium
2026-04-24 11:49 |  | DEVS-41 | 91:16 | Epic | 91:16 | Reporting & Analytics | 91:16 | Emily Johnson | 91:15 | TO DO |  | 91:16 | 2026-12-31 |  | 91:15 | Medium |  | 91:16
2026-04-20 16:33 | Emily Johnson | DEVS-41 |  | Epic |  | Reporting & Analytics |  | Unassigned | 0:00 | TO DO |  |  | 2026-12-31 |  |  | Medium
2026-04-20 16:33 | Emily Johnson | DEVS-41 |  | Epic |  | Reporting & Analytics |  | Unassigned |  | TO DO |  |  |  | 2026-12-31 | 0:00 | Medium
2026-04-20 16:33 | Emily Johnson | DEVS-41 |  | Epic |  | Reporting & Analytics |  | Unassigned |  | TO DO | [5 empty] | Medium
2026-04-24 11:49 |  | DEVS-40 | 91:16 | Epic | 91:16 | Payment Integration | 91:16 | Emily Johnson | 91:16 | TO DO |  | 91:16 | 2026-07-31 |  | 91:16 | Medium |  | 91:16
2026-04-20 16:33 | Emily Johnson | DEVS-40 |  | Epic |  | Payment Integration |  | Emily Johnson |  | TO DO |  |  |  | 2026-07-31 | 0:00 | Medium
2026-04-20 16:33 | Emily Johnson | DEVS-40 |  | Epic |  | Payment Integration |  | Unassigned | 0:00 | TO DO | [5 empty] | Medium
2026-04-20 16:32 | Emily Johnson | DEVS-40 |  | Epic |  | Payment Integration |  | Unassigned |  | TO DO | [5 empty] | Medium
2026-04-24 11:49 |  | DEVS-39 | 91:17 | Epic | 91:17 | User Profile Management | 91:17 | Cody Fisher | 91:17 | TO DO |  | 91:17 | 2026-05-31 |  | 91:16 | Medium |  | 91:17
2026-04-20 16:32 | Emily Johnson | DEVS-39 |  | Epic |  | User Profile Management |  | Cody Fisher |  | TO DO |  |  |  | 2026-05-31 | 0:01 | Medium
2026-04-20 16:32 | Emily Johnson | DEVS-39 |  | Epic |  | User Profile Management |  | Unassigned | 0:00 | TO DO | [5 empty] | Medium
2026-04-20 16:32 | Emily Johnson | DEVS-39 |  | Epic |  | User Profile Management |  | Unassigned |  | TO DO | [5 empty] | Medium
2026-04-24 11:49 |  | DEVS-38 | 91:19 | Epic | 91:19 | User Authentication & Authorization | 91:19 | Emily Johnson | 91:18 | TO DO |  | 91:19 | 2026-06-30 |  | 91:18 | Medium |  | 91:19
2026-04-20 16:30 | Emily Johnson | DEVS-38 |  | Epic |  | User Authentication & Authorization |  | Emily Johnson |  | TO DO |  |  |  | 2026-06-30 | 0:01 | Medium
2026-04-20 16:30 | Emily Johnson | DEVS-38 |  | Epic |  | User Authentication & Authorization |  | Unassigned | 0:00 | TO DO | [5 empty] | Medium
2026-04-20 16:30 | Emily Johnson | DEVS-38 |  | Epic |  | User Authentication & Authorization |  | Unassigned |  | TO DO | [5 empty] | Medium
2026-04-24 11:49 |  | DEVS-33 | 2518:56 | Task | 2518:56 | Investigate Payment Failure for Customer | 2518:56 | Emily Johnson | 2518:56 | DONE |  | 70:08 | 2026-04-30 |  | 91:12 | High |  | 2518:56
2026-04-21 13:40 | Emily Johnson | DEVS-33 |  | Task |  | Investigate Payment Failure for Customer |  | Emily Johnson |  | REOPENED | DONE | 19:53 | 2026-04-30 |  |  | High
2026-04-20 17:47 | Emily Johnson | DEVS-33 |  | Task |  | Investigate Payment Failure for Customer |  | Emily Johnson |  | DONE | REOPENED | 1:05 | 2026-04-30 |  |  | High
2026-04-20 16:42 | Cody Fisher | DEVS-33 |  | Task |  | Investigate Payment Failure for Customer |  | Emily Johnson |  | REOPENED | DONE | 0:03 | 2026-04-30 |  |  | High
2026-04-20 16:39 | Emily Johnson | DEVS-33 |  | Task |  | Investigate Payment Failure for Customer |  | Emily Johnson |  | DONE | REOPENED | 0:00 | 2026-04-30 |  |  | High
2026-04-20 16:39 | Emily Johnson | DEVS-33 |  | Task |  | Investigate Payment Failure for Customer |  | Emily Johnson |  | IN PROGRESS | DONE | 2426:48 | 2026-04-30 |  |  | High
2026-04-20 16:37 | Emily Johnson | DEVS-33 |  | Task |  | Investigate Payment Failure for Customer |  | Emily Johnson |  | IN PROGRESS |  |  |  | 2026-04-30 | 2427:44 | High
2026-04-24 11:49 |  | DEVS-31 | 2518:57 | Task | 2518:57 | Integrate Payment Gateway API | 2518:57 | Cody Fisher | 2518:57 | IN PROGRESS |  | 91:09 | 2026-05-08 |  | 89:38 | High |  | 91:11
2026-04-20 18:11 | Cody Fisher | DEVS-31 |  | Task |  | Integrate Payment Gateway API |  | Cody Fisher |  | IN PROGRESS |  |  | 2026-04-30 | 2026-05-08 | 1:33 | High
2026-04-20 16:40 | Cody Fisher | DEVS-31 |  | Task |  | Integrate Payment Gateway API |  | Cody Fisher |  | TO DO | IN PROGRESS | 2427:48 | 2026-04-30 |  |  | High
2026-04-20 16:38 | Emily Johnson | DEVS-31 |  | Task |  | Integrate Payment Gateway API |  | Cody Fisher |  | TO DO |  |  | 2026-04-30 |  |  | Medium | High | 2427:46
2026-04-20 16:38 | Emily Johnson | DEVS-31 |  | Task |  | Integrate Payment Gateway API |  | Cody Fisher |  | TO DO |  |  | 2026-01-15 | 2026-04-30 | 2427:46 | Medium
2026-04-24 11:49 |  | DEVS-29 | 2612:29 | Task | 2612:29 | Strengthen Security & Data Protection | 2612:29 | Cody Fisher | 2612:29 | TO DO |  | 2612:29 | 2026-05-29 |  | 91:11 | Medium |  | 2612:29
2026-04-20 16:37 | Emily Johnson | DEVS-29 |  | Task |  | Strengthen Security & Data Protection |  | Cody Fisher |  | TO DO |  |  |  | 2026-05-29 | 2521:18 | Medium
2026-04-24 11:49 |  | DEVS-28 | 2612:30 | Task | 2612:30 | Improve Application Performance | 2612:30 | Emily Johnson | 91:12 | TO DO |  | 2612:30 | 2026-05-29 |  | 91:12 | Medium |  | 2612:30
2026-04-20 16:37 | Emily Johnson | DEVS-28 |  | Task |  | Improve Application Performance |  | Cody Fisher | 2521:18 | TO DO |  |  | 2026-05-29 |  |  | Medium
2026-04-20 16:37 | Emily Johnson | DEVS-28 |  | Task |  | Improve Application Performance |  | Cody Fisher |  | TO DO |  |  | 2026-01-13 | 2026-05-29 | 2521:18 | Medium
2026-04-24 11:49 |  | DEVS-26 | 3353:54 | Task | 3353:54 | Update billing system for instant upgrades | 3353:54 | James Smith | 3353:54 | DONE |  | 91:09 | 2026-04-30 |  | 91:13 | Highest |  | 3353:54
2026-04-20 16:39 | Emily Johnson | DEVS-26 |  | Task |  | Update billing system for instant upgrades |  | James Smith |  | IN PROGRESS | DONE | 2521:19 | 2026-04-30 |  |  | Highest
2026-04-20 16:36 | Emily Johnson | DEVS-26 |  | Task |  | Update billing system for instant upgrades |  | James Smith |  | IN PROGRESS |  |  | 2026-01-30 | 2026-04-30 | 2427:39 | Highest
2026-04-24 11:49 |  | DEVS-25 | 3353:55 | Task | 3353:55 | Implement frontend UI and connect it to backend | 3353:55 | James Smith | 3353:55 | IN PROGRESS |  | 2612:34 | 2026-05-30 |  | 91:13 | High |  | 3353:55
2026-04-20 16:36 | Emily Johnson | DEVS-25 |  | Task |  | Implement frontend UI and connect it to backend |  | James Smith |  | IN PROGRESS |  |  | 2026-01-23 | 2026-05-30 | 2521:21 | High

## Field changes total count
Work item | Key | Issue Type | Summary | Assignee | Status | Due date | Priority | Total, q-ty
DEVS-48 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
DEVS-47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DEVS-46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DEVS-45 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2
DEVS-44 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 3
DEVS-43 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2
DEVS-42 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2
DEVS-41 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2
DEVS-40 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2
DEVS-39 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2
DEVS-38 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2
DEVS-33 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 6
DEVS-31 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 4
DEVS-29 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
DEVS-28 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2
DEVS-26 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2
DEVS-25 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Total, q-ty | 0 | 0 | 0 | 8 | 10 | 14 | 2 | 34

## Time in field values
| Issue Type |  |  | Summary | Assignee |  |  |  |  | Status |  |  |  |  | Due date | Priority
Work item | Epic | Task | Total | Field type is not supported | Cody Fisher | Emily Johnson | James Smith | Unassigned | Total | DONE | IN PROGRESS | REOPENED | TO DO | Total | Field type is not supported | Highest | High | Medium | Low | Total
DEVS-48 | 0:00 | 91:05 | 91:05 | - | 0:00 | 91:05 | 0:00 | 0:00 | 91:05 | 0:00 | 70:08 | 0:00 | 20:56 | 91:05 | - | 0:00 | 91:05 | 0:00 | 0:00 | 91:05
DEVS-47 | 0:00 | 91:05 | 91:05 | - | 91:05 | 0:00 | 0:00 | 0:00 | 91:05 | 0:00 | 0:00 | 0:00 | 91:05 | 91:05 | - | 0:00 | 0:00 | 0:00 | 91:05 | 91:05
DEVS-46 | 0:00 | 91:07 | 91:07 | - | 91:07 | 0:00 | 0:00 | 0:00 | 91:07 | 0:00 | 0:00 | 0:00 | 91:07 | 91:07 | - | 0:00 | 0:00 | 91:07 | 0:00 | 91:07
DEVS-45 | 0:00 | 91:08 | 91:08 | - | 91:08 | 0:00 | 0:00 | 0:00 | 91:08 | 0:00 | 91:08 | 0:00 | 0:00 | 91:08 | - | 0:00 | 0:00 | 91:08 | 0:00 | 91:08
DEVS-44 | 0:00 | 91:10 | 91:10 | - | 89:57 | 1:13 | 0:00 | 0:00 | 91:10 | 0:00 | 91:10 | 0:00 | 0:00 | 91:10 | - | 0:00 | 89:56 | 1:13 | 0:00 | 91:10
DEVS-43 | 91:14 | 0:00 | 91:14 | - | 0:00 | 91:14 | 0:00 | 0:00 | 91:14 | 0:00 | 0:00 | 0:00 | 91:14 | 91:14 | - | 0:00 | 0:00 | 91:14 | 0:00 | 91:14
DEVS-42 | 91:15 | 0:00 | 91:15 | - | 91:15 | 0:00 | 0:00 | 0:00 | 91:15 | 0:00 | 0:00 | 0:00 | 91:15 | 91:15 | - | 0:00 | 0:00 | 91:15 | 0:00 | 91:15
DEVS-41 | 91:16 | 0:00 | 91:16 | - | 0:00 | 91:15 | 0:00 | 0:00 | 91:16 | 0:00 | 0:00 | 0:00 | 91:16 | 91:16 | - | 0:00 | 0:00 | 91:16 | 0:00 | 91:16
DEVS-40 | 91:16 | 0:00 | 91:16 | - | 0:00 | 91:16 | 0:00 | 0:00 | 91:16 | 0:00 | 0:00 | 0:00 | 91:16 | 91:16 | - | 0:00 | 0:00 | 91:16 | 0:00 | 91:16
DEVS-39 | 91:17 | 0:00 | 91:17 | - | 91:17 | 0:00 | 0:00 | 0:00 | 91:17 | 0:00 | 0:00 | 0:00 | 91:17 | 91:17 | - | 0:00 | 0:00 | 91:17 | 0:00 | 91:17
DEVS-38 | 91:19 | 0:00 | 91:19 | - | 0:00 | 91:18 | 0:00 | 0:00 | 91:19 | 0:00 | 0:00 | 0:00 | 91:19 | 91:19 | - | 0:00 | 0:00 | 91:19 | 0:00 | 91:19
DEVS-33 | 0:00 | 131:49 | 131:49 | - | 0:00 | 131:49 | 0:00 | 0:00 | 131:49 | 71:13 | 40:39 | 19:56 | 0:00 | 131:49 | - | 0:00 | 131:49 | 0:00 | 0:00 | 131:49
DEVS-31 | 0:00 | 131:49 | 131:49 | - | 131:49 | 0:00 | 0:00 | 0:00 | 131:49 | 0:00 | 91:09 | 0:00 | 40:40 | 131:49 | - | 0:00 | 91:11 | 40:38 | 0:00 | 131:49
DEVS-29 | 0:00 | 131:49 | 131:49 | - | 131:49 | 0:00 | 0:00 | 0:00 | 131:49 | 0:00 | 0:00 | 0:00 | 131:49 | 131:49 | - | 0:00 | 0:00 | 131:49 | 0:00 | 131:49
DEVS-28 | 0:00 | 131:49 | 131:49 | - | 40:37 | 91:12 | 0:00 | 0:00 | 131:49 | 0:00 | 0:00 | 0:00 | 131:49 | 131:49 | - | 0:00 | 0:00 | 131:49 | 0:00 | 131:49
DEVS-26 | 0:00 | 131:49 | 131:49 | - | 0:00 | 0:00 | 131:49 | 0:00 | 131:49 | 91:09 | 40:39 | 0:00 | 0:00 | 131:49 | - | 131:49 | 0:00 | 0:00 | 0:00 | 131:49
DEVS-25 | 0:00 | 131:49 | 131:49 | - | 0:00 | 0:00 | 131:49 | 0:00 | 131:49 | 0:00 | 131:49 | 0:00 | 0:00 | 131:49 | - | 0:00 | 131:49 | 0:00 | 0:00 | 131:49

## Count of field values
| Issue Type |  |  | Summary | Assignee |  |  |  |  | Status |  |  |  |  | Due date | Priority
Work item | Epic | Task | Total | Field type is not supported | Cody Fisher | Emily Johnson | James Smith | Unassigned | Total | DONE | IN PROGRESS | REOPENED | TO DO | Total | Field type is not supported | Highest | High | Medium | Low | Total
DEVS-48 | 0 | 1 | 1 | - | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 2 | - | 0 | 1 | 0 | 0 | 1
DEVS-47 | 0 | 1 | 1 | - | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | - | 0 | 0 | 0 | 1 | 1
DEVS-46 | 0 | 1 | 1 | - | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | - | 0 | 0 | 1 | 0 | 1
DEVS-45 | 0 | 1 | 1 | - | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 2 | - | 0 | 0 | 1 | 0 | 1
DEVS-44 | 0 | 1 | 1 | - | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 2 | - | 0 | 1 | 1 | 0 | 2
DEVS-43 | 1 | 0 | 1 | - | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 1 | 1 | - | 0 | 0 | 1 | 0 | 1
DEVS-42 | 1 | 0 | 1 | - | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 1 | 1 | - | 0 | 0 | 1 | 0 | 1
DEVS-41 | 1 | 0 | 1 | - | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 1 | 1 | - | 0 | 0 | 1 | 0 | 1
DEVS-40 | 1 | 0 | 1 | - | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 1 | 1 | - | 0 | 0 | 1 | 0 | 1
DEVS-39 | 1 | 0 | 1 | - | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 1 | 1 | - | 0 | 0 | 1 | 0 | 1
DEVS-38 | 1 | 0 | 1 | - | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 1 | 1 | - | 0 | 0 | 1 | 0 | 1
DEVS-33 | 0 | 1 | 1 | - | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 2 | 0 | 6 | - | 0 | 1 | 0 | 0 | 1
DEVS-31 | 0 | 1 | 1 | - | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 2 | - | 0 | 1 | 1 | 0 | 2
DEVS-29 | 0 | 1 | 1 | - | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | - | 0 | 0 | 1 | 0 | 1
DEVS-28 | 0 | 1 | 1 | - | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1 | - | 0 | 0 | 1 | 0 | 1
DEVS-26 | 0 | 1 | 1 | - | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 2 | - | 1 | 0 | 0 | 0 | 1
DEVS-25 | 0 | 1 | 1 | - | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | - | 0 | 1 | 0 | 0 | 1

## Export settings
Setting | Info
Organization | reklamanataliak.atlassian.net
Exported Time | April 24, 2026 at 11:48 AM (+03:00)
Exported By | Emily Johnson
Page | Main page
Active Mode | Table View
Space | DEVS [DEVS]
Updated By | Any User
Date Range From | 04/19/2026
Date Range To | 04/25/2026
Sort Order | Date of change - ↓ (DESC), Key - ↓ (DESC)
Work Item Filter | None
Transition Filters | None
Work Items | 17
Changes | 45
Time Format | Pretty (Example - "3 days, 7 hours, 45 minutes")